## Sheet1
Task | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Legend
Initial Project Meeting | [33 empty] | Literature/ Source Finding | bar: January W2
Lietrature review: Current methods | [33 empty] | OSC modelling | bar: January W2 to February W4
Literature review: Applications relevant to study | [33 empty] | Writing | bar: January W2 to February W4
Building the model in OSC | [33 empty] | Coding/ Data Analysis | bar: January W4 to February W3; August W2
Adding external force on model | [33 empty] | Deadline | bar: February W2 to February W3
Including muscle contractions | [33 empty] | Break/ Exams | bar: February W3
Working on planning report | bar: January W3 to March W1
Model Validation | bar: March W1 to March W2
Acquire mechanical properties of HT tendon graft | bar: March W1 to March W3
Acquire realistic movements to test on model | bar: March W4 to April W1
Determine which muscle model to use (Thelen2003 or Millard2012) | bar: April W2 to April W3
Determine biomechanical unnatural movemements | bar: April W3
Implement movements into the model | bar: April W4
Create Force-strain charts to be used in optimisation | bar: June W1 to June W2
Develop optimisation procedure to determine optimal initial fixation strength as a function of graft stiffness | bar: June W2 to June W4
Result Processing | bar: July W1 to July W3
Final Report Write up | bar: June W3 to August W3
Defence | bar: August W3 to August W4
𝜃_(𝑟𝑜𝑡, 𝑚𝑎𝑥)